## Sheet1
Purpose of website: Objective to learn how to start building a website, from start to finish, using software such as visual studio and sublime text, adding details to itsuch as images, text and website links. A smart target is set to the project. Outcome of project: A completed website with all required features, that functions, looks good and complies with all web developing guidelines.
| Days 1 | Days 2 | Days 3 | Days 4 | Days 5 | Days 6 | Days 7 | Days 8 | Days 9 | Days 10 | Days 11 | Days 12 | Days 13 | Days 14 | Days 15 | Days 16 | Days 17 | Days 18 | Days 19 | Days 20 | Days 21
Produce requirements of project | bar: Days 1 to Days 2
Produce website concept | bar: Days 2 to Days 3
Wire diagrams of web pages | bar: Days 4
Produce skeleton web pages | bar: Days 5 to Days 7
Gather images for web pages | bar: Days 7 to Days 8
Produce a header image for web pages | bar: Days 9
Produce text for web pages | bar: Days 10 to Days 11
Crop images for web pages | bar: Days 12
Produce own content in paint | bar: Days 13
Produce style for content | bar: Days 13 to Days 14
Add content to web pges with consistent look and feel | bar: Days 15 to Days 16
Produce navigation for web pges | bar: Days 16
Check web pages to functionality | bar: Days 17
Check markup | bar: Days 17
Check css | bar: Days 17
Test website | bar: Days 18
Upload to hosting website | bar: Days 19
Test website, using host website | bar: Days 20 to Days 21